## Sheet1
Resource | 2017-04-27 | 2017-04-28 | 2017-05-01 | 2017-05-02 | 2017-05-03 | 2017-05-04 | 2017-05-05 | 2017-05-06 | 2017-05-07 | 2017-05-08 | 2017-05-09 | 2017-05-10 | 2017-05-11 | 2017-05-12 | 2017-05-13 | 2017-05-14 | 2017-05-15
Milind Roy | 2017-04-27: Leave; 2017-04-28: Leave; 2017-05-01: Holiday; 2017-05-06: Weekend
Sreenu Banoth | 2017-04-27: Due to machine issue, CCD team changed the machine and Visual Studio 2015 and SQL server installation completed.; 2017-04-28: Following up with CCD team to install GitHub and VS 2017. Once installation completed I will start work Service tab functionality.; 2017-05-03: Created service Tab page Type script,html files under Model & service folder and also created service json file with required fields. Now service line page is loaded successfully in Crest application.; 2017-05-04: I have completed Data binding in service tab in grid page from the service (mock data).; 2017-05-05: I have started work on auto complete search functionality to perform the search criteria in UI-service tab and the work in progressing.; 2017-05-08: I have completed auto complete functionality in service tab.Now search criteria is working fine.
Gottam Mahender | 2017-04-27: Worked on: I started working on Application tab and following functionality are completed Auto Complete for Application, Contract Id and Service line using AngularJS2 and VS 2015.; 2017-04-28: VS 2017 installation completed and clone the latest code from GitHub. In Progress: Will integrate the Auto Complete functionality in Application tab to VS 2017. Then need to start work on Find button functionality.; 2017-05-02: Worked on Autocomplete integration.; 2017-05-03: Autocomplete functionality integrated and search functionality implemented within GitHub solution .; 2017-05-04: I have fixed css loading issue.; 2017-05-05: I have created GitHub repository and pushed the latest updated UI-Application design.; 2017-05-08: Working on application add functionality under UI-Application Tab.
Ponna Shiva Prasad | 2017-04-27: Completed: 1. Installed VS 2017 and created Web API application using .Net core with Entity Framework 2. DB insertion for SoW and Supplier tables from excel sheet to fetch data using entity framework. In-Progress: Will start work on Web API functionality to fetch the data using Data Access layer structure.; 2017-04-28: Will start work on Web API functionality to fetch the data using Data Access layer structure.; 2017-05-03: To get the data from Supplier table using Entity Framework with Repository and Interface classes.
Kumar Ravi Shekhar | 2017-04-27: There were discrepancy in the database schema as it was developed based on the old excel sheet template, but now we have to work based on the new excel sheet, so I discussed with Supraja and I am going through the new changes.; 2017-04-28: Currently I am analyzing the excel sheet data and schema and preparing data for few columns which are required for insertion but not present in excel sheet, since there were changes in the old templates and the new one.; 2017-05-02: Making modifications in the Database schema based on the new Excel Sheet and prepared final data in the excel sheet based on the different constraints that needs to be inserted in the database.; 2017-05-03: Making modifications in the Database schema based on the new Excel Sheet and prepared final data in the excel sheet based on the different constraints that needs to be inserted in the database.; 2017-05-04: In Progress. Making changes in schema.; 2017-05-05: Schema updated and January data inserted in SOW, Service & Application Table.; 2017-05-08: Database Schema completed and Insertion of data completed for January.
Vankayalapati Naveen | 2017-04-27: Completed: Restored DB back up file in local machine and started working on Stored Procedure creation. Insert, update and delete stored procedures are completed from SoW table In Progress: Need to test stored procedure and will start other stored procedure creation.; 2017-04-28: Leave; 2017-05-02: Leave; 2017-05-03: Created and tested SP for SoW insert and update. Working fine.; 2017-05-04: Sent SP code to Supraja and given answers to her questions. I will change the SP code based on supraja’s reply.; 2017-05-05: Changed the SP code as per supraja's suggestions.waiting for Kumar mail related to updated db schema.
Avni Dixit | 2017-04-27: Cloned project from GitHub and understanding project structure.; 2017-04-28: Need to start work on SoW tab. Now I got the basic idea of app module and component. Github extension installation is pending because I don’t have admin rights CCD team is not giving rights even after DM approval. Discussion is going on. As of now I raised AHD for GitHub extension installation that will take 1-2 days; 2017-05-02: Worked on- Installed Github extension for VS. Also got admin rights. In Progress- Started working on SoW tab UI. Today I worked on CSS and Angular 2 component flow. Sent separate mail to Supraja regarding few doubts.; 2017-05-03: Started working on SoW UI. Need to discuss few things related to bootstrap css , github and project requirement.; 2017-05-04: Yesterday doubts are clarified by Mahender. Will proceed further.; 2017-05-05: Going through typescript code and flow.; 2017-05-08: Understood the whole flow of data. Started working on code.
Supraja Tatichetla | 2017-04-27: Worked-on: Have worked on SOW landing page. Github setup and have checked-in the code In-Progress: Will start working on Service Level performance page in UI; 2017-04-28: Working on SLP screen; 2017-05-02: Implemented routing for SLP page; 2017-05-03: Designing SLP UI page; 2017-05-04: Doing analysis on which grid will suit SLP page requirement; 2017-05-05: Working on to integrate handson table in SLP page